## Summary
Commercial construct — two-year delivery envelope + one-year AMC |  | USD
1 · Platform licence (the built platform, both portals) | Derived: target minus all other components — see implied effort below | 1676563
2 · Delta development (70:30 offshore/onshore) | 218 person-months per DeltaDev | 2171290
3 · Contingency on development | Rate below | 217129
4 · Training delivery (non-labour) | OtherCosts | 60000
5 · Travel, lodging & boarding | TravelLodging | 372018
6 · Software licences & tooling | OtherCosts | 160000
7 · Local compliance & certification | OtherCosts | 95000
8 · Miscellaneous & mobilisation + optional cloud | OtherCosts | 80000
9 · AMC — Year 1 | AMC sheet (per-year price; client may extend at the escalation table) | 568000
TOTAL |  | 5400000
Total Final Commercials | Fixed commercial target | 5400000
Contingency rate | editable | 10%

## RateCards
Role | Offshore rate (USD/mo) | Onshore UAE rate (USD/mo) | Notes
Programme Manager | 9500 | 21000 | Client-facing governance — onshore-led
Solution Architect | 11000 | 24000 | Onshore for design and drop windows
Technical Lead | 8000 | 17500 | Workstream leads; onshore rotations
Senior Engineer | 6500 | 14500 | Platform and domain services
Engineer | 4800 | 11000 | Feature build — offshore
AI/ML Engineer | 8500 | 19000 | Agents, models, evaluation
QA Engineer | 4200 | 9500 | Automation-first; onshore for UAT
DevOps Engineer | 6500 | 14500 | Chassis, CI/CD, environments
BA / Domain SME | 5500 | 13000 | Ministry workshops, UAT — onshore-led
Support Engineer (AMC L2/L3) | 6500 | 14500 | Post-go-live support pod
Service Delivery Manager (AMC) | 9500 | 21000 | AMC governance, SLA reporting
NOTE: onshore rates are labour only — lodging, boarding and travel are costed separately in this model.

## DeltaDev
Role (FTE per window) | M0–M2 | M3–M5 | M6–M8 | M9–M11 | M12–M14 | M15 | Person-months | Onshore share | Onshore MM | Offshore MM | Onshore cost | Offshore cost | Role cost
Programme Manager | 1 | 1 | 1 | 1 | 1 | 1 | 16 | 100% | 16 | 0 | 336000 | 0 | 336000
Solution Architect | 1 | 1 | 1 | 1 | 0.5 | 0 | 13.5 | 60% | 8.1 | 5.4 | 194400 | 59400 | 253800
Technical Lead | 1 | 2 | 3 | 3 | 2 | 1 | 34 | 40% | 13.6 | 20.4 | 238000 | 163200 | 401200
Senior Engineer | 2 | 4 | 5 | 5 | 3 | 2 | 59 | 20% | 11.8 | 47.2 | 171100 | 306800 | 477900
Engineer | 1 | 2 | 3 | 3 | 2 | 1 | 34 | 0% | 0 | 34 | 0 | 163200 | 163200
AI/ML Engineer | 1 | 2 | 2 | 2 | 1.5 | 0.5 | 26 | 25% | 6.5 | 19.5 | 123500 | 165750 | 289250
QA Engineer | 0 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 18 | 10% | 1.8 | 16.2 | 17100 | 68040 | 85140
DevOps Engineer | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 11 | 10% | 1.1 | 9.9 | 15950 | 64350 | 80300
BA / Domain SME | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 6.5 | 100% | 6.5 | 0 | 84500 | 0 | 84500
Total | 8 | 14 | 18 | 18 | 12 | 8 | 218 |  | 65.4 | 152.6 | 1180550 | 990740 | 2171290
Onshore share of MM (target 30%) | [7 empty] | 30%

## AMC
AMC support pod (per year) | FTE | Location | Rate (USD/mo) | Months | Cost (USD)
Support Engineer (AMC L2/L3) | 3 | Offshore | 6500 | 12 | 234000
Support Engineer (AMC L2/L3) | 0.5 | Onshore | 14500 | 12 | 87000
AI/ML Engineer | 0.5 | Offshore | 8500 | 12 | 51000
DevOps Engineer | 0.5 | Offshore | 6500 | 12 | 39000
Service Delivery Manager (AMC) | 0.5 | Onshore | 21000 | 12 | 126000
Tooling, monitoring & SLA reporting stack |  |  |  |  | 31000
AMC Year-1 price |  |  |  |  | 568000
Covers: 24/7 P1 support per RFP §6.1 SLAs · model drift monitoring (§6.6) · quarterly AI adoption reporting (D12) · patches per §6.5 clocks
Extension pricing (client option): | Years | Escalation p.a. | Price
Year 2 | 2 | 3% | 585040
Year 3 | 3 | 3% | 602591.2
Year 4 | 4 | 3% | 620668.936
Year 5 | 5 | 3% | 639289.0041
AMC Year 1 runs twelve months from hypercare exit (end M18); instalments are billed quarterly in arrears from that date.

## TravelLodging
Item | Qty | Unit | Rate (USD) | Cost (USD)
Return flights (rotations, mobilisation, leadership reviews) | 70 | trips | 1200 | 84000
Lodging & boarding — onshore stays | 65.4 | person-months | 3670 | 240018
Local transport & UAE mobility |  | lump sum |  | 24000
Visas & work permits | 30 | permits | 800 | 24000
Total travel, lodging & boarding |  |  |  | 372018
Lodging basis: serviced apartment ~2,700 + boarding per-diem ~970 per onshore person-month. Onshore labour rates in RateCards exclude these.

## OtherCosts
Item | Detail | Cost (USD)
Training delivery (non-labour) | Bilingual AR/EN materials, translation, training lab environments, venues; trainer effort is inside the development estimate (D10) | 60000
Software licences & tooling (delivery period) | APM/monitoring, code quality, test & load tooling, design/collab licences for the programme team | 160000
Local compliance & certification | UAE-accredited VAPT (annual, §6.5), TDRA accessibility audit (§5.9), PDPL/data-residency advisory, security-standards alignment (§7.4) | 95000
Miscellaneous & mobilisation | Insurance, communications, logistics, workspace, mobilisation/demobilisation | 80000
Cloud consumption (optional — default client-side) | Azure subscription assumed held by the Authority; set a value here only if vendor-carried | 0
Total other costs |  | 395000

## Milestones
Payment schedule |  |  | Delivery price (total minus AMC): | 4832000
# | Milestone | When | Share | USD
1 | Contract signature & mobilisation | M0 | 10% | 483200
2 | Architecture & design baseline (D1) accepted | M5 | 10% | 483200
3 | Drop 1 accepted — MDM, Ships, Legislation; A1/A3/A4/A6; UAE PASS | M7 | 15% | 724800
4 | Drop 2 accepted — Seafarers, NMC live feeds, Smart Inspection + inspector app; A2/A5/A7 | M11 | 15% | 724800
5 | Drop 3 accepted — Ports, Facilities, Revenue + gateway; dashboards; customer app; LCNC GA | M14 | 15% | 724800
6 | Migration approved & UAT complete | M15 | 10% | 483200
7 | Go-Live (T0) | end M15 | 15% | 724800
8 | Hypercare exit & operational handover | M18 | 10% | 483200
| Delivery milestones total |  | 100% | 4832000
AMC Year 1 — billed quarterly in arrears from AMC start (hypercare exit, end M18)
| Quarter 1 | AMC month 1–3 |  | 142000
| Quarter 2 | AMC month 4–6 |  | 142000
| Quarter 3 | AMC month 7–9 |  | 142000
| Quarter 4 | AMC month 10–12 |  | 142000
| GRAND TOTAL — delivery + AMC Year 1 |  |  | 5400000
| Check vs target price (should be 0) |  |  | 0