MARITIME TRANSFORMATION PROGRAMME

Commercial Proposal

Unified Maritime Digital Services Platform

A working platform, a costed and time-boxed transformation, and a governed AI operating model — offered as one commercial construct: a two-year delivery envelope with one year of managed support, at a fixed price of USD 5.40 million.

| Document control |  |
| --- | --- |
| Classification | CONFIDENTIAL — commercial in confidence |
| Version / Date | Proposal V1 · August 2026 |
| Validity | 90 days from date of issue; prices firm for an award within the validity period |
| Method | Commercial companion to the Technical Approach Document (V15) and the Sagar Drishti TAD (V1). Prices from the commercial model workbook (Annexure C); the annexure register is in Section 7. |
| Alignment | Target stack aligned to the Client's shared Azure platform architecture: Microsoft Foundry Agent Service AI layer, AKS microservices, ADLS Gen2 + AI Search data/AI foundation, Entra ID + UAE PASS identity, UAE North / UAE Central regions |
| Baseline evidence | A working 13-module maritime operations platform and a companion AI analytics portal (live demo available); production reference architecture on Azure in operation |
| Estimate status | Effort estimates indicative at line level, to be confirmed at D0/D1; the price is fixed within the stated scope envelope, with movement beyond it handled by change control |

How to read this proposal: every capability claimed is running today and photographed in the accompanying Technical Approach Document (V15); every number quoted reconciles to the commercial model workbook (CommercialModel-V1.xlsx, Annexure C), where every rate and share is an editable parameter.

# Contents

1.  Executive summary	2

2.  What the price buys — the construct in detail	2

2.1  The platform licence — USD 1,676,563	2

2.2  The transformation programme — USD 2,171,290 plus 10% contingency	3

2.3  Delivery costs — USD 767,018	3

2.4  Managed support — AMC Year 1, USD 568,000	4

3.  How it is delivered	4

4.  Payment schedule	5

5.  Assumptions, exclusions and dependencies	5

6.  Why this offer is credible	6

7.  Offer terms, validity and annexures	6

# 1.  Executive summary

The Client is buying three things, and only one of them is still to be built. The first is a working platform: a maritime administration system covering all seven RFP domains — ships, seafarers, legislation, the National Maritime Centre, smart inspection, ports and marine facilities — with seven governed AI agents deciding on its own records today, and an AI analytics portal beside it. It exists, it runs, and the accompanying Technical Approach Document photographs it screen by screen. The second is the transformation from that platform to the Client’s full target: every RFP requirement closed, the application re-architected as microservices, scaled to country level across multiple ports, fully bilingual in Arabic and English, agentic AI at the centre of every service, and a no-code/low-code configuration studio — delivered drop-wise in fourteen months of development with go-live at month fifteen. The third is certainty of operation: a staffed, SLA-backed year of managed support after go-live, extendable at the Client’s option.

The commercial construct is deliberately simple:

| The offer | USD |
| --- | --- |
| The platform — licence for the built estate (both applications) | 1,676,563 |
| The transformation — the complete delta programme, delivered drop-wise, with contingency | 2,388,419 |
| Delivery costs — training, travel and local presence, licences, UAE compliance, miscellaneous | 767,018 |
| Managed support — AMC Year 1, 24/7 SLA-backed | 568,000 |
| Total — two-year delivery envelope plus one year of support | 5,400,000 |

Three properties of this offer are worth stating up front. It starts from software, not slideware — evaluation can begin with a login, not a workshop. Its price is fixed, with an open model behind it: every rate, share and quantity is an editable parameter in the commercial workbook, and the construct re-reconciles automatically. And its risk is lower than the ambition suggests: the foundation is already built, so the delta programme spends its fourteen months on the Client’s specific requirements rather than on reinventing a registry platform.

# 2.  What the price buys — the construct in detail

## 2.1  The platform licence — USD 1,676,563

The licence covers the built estate as documented and photographed in the Technical Approach Document: the operations platform — thirteen modules, 207 REST endpoints, 26 data models, deny-by-default RBAC over 24 permission groups, an audit register spanning every write, seven mandated AI agents with 79 recorded decisions under a governed autonomy model — and the Sagar Drishti analytics portal with its nine-agent analyst workforce, grounded assistant, three-language interface and 3D port twin. The licence price reflects the embodied build: roughly 240 person-months (about 1,040 man-weeks) of prior engineering, priced at the blended offshore rate of the delivery team — USD 6,990 per person-month, derived in the commercial workbook — and unlike an estimate, the estate it prices can be inspected before signature.

Scope: single-authority national deployment, all environments, both applications.

The licence is what makes a fourteen-month transformation credible: the delta programme starts from working software carrying an automated regression suite of 79 tests over the domain rules and API, and a seeded reference world — not from analysis.

## 2.2  The transformation programme — USD 2,171,290 plus 10% contingency

The complete delta between the platform as it stands and the Client’s target, consolidated in Section 15 of the Technical Approach Document: 944 man-weeks — 218 person-months — decomposed to testable line items across every module and every agent, plus the five transformation streams the Client has directed:

| Programme component | MW |
| --- | --- |
| RFP domain and platform-module deltas (TAD Sections 3–13) | 520 |
| Agentic AI across the platform — the seven agents to full RFP capability (TAD Section 14) | 174 |
| Microservices re-architecture along the platform’s documented seams | 90 |
| Country-level, multi-port operation (tenancy, national registries, onboarding) | 40 |
| Full Arabic/English multilingual with RTL | 18 |
| Agentic AI at the centre — coverage rollout toward the 80% target | 24 |
| No-code/low-code configuration studio | 26 |
| Customer mobile application (inspector app is inside the domain deltas) | 24 |
| Programme delivery — data readiness, migration, UAT and hypercare, training effort | 28 |
| Consolidated programme | 944 |

Delivery runs 70:30 offshore/onshore: the build from the offshore centre; programme leadership, architecture windows, ministry workshops, UAT and training onshore with the Client. The team ramps from 8 to a peak of 18 and back to 8 across sixteen months. A contingency of 10% is held against the development estimate inside the fixed price — it is the System Integrator’s risk provision, not an additional charge to the Client.

A note for the reader holding both documents: Section 16.7 of the Technical Approach Document is the earlier, effort-only sizing of this same programme — identical effort and rates, but with a 12% planning contingency and international travel treated as pass-through (its basis is the sizing workbook, Annexure D). This proposal supersedes that indicative view: the 10% contingency, the firm travel and lodging lines, and the totals stated here are the commercial terms.

## 2.3  Delivery costs — USD 767,018

| Line | What it covers | USD |
| --- | --- | --- |
| Training delivery | Bilingual Arabic/English materials, translation, training-lab environments and venues. Trainer effort itself is inside the development estimate — this line is the non-labour cost of doing it properly. | 60,000 |
| Travel | Seventy return rotations across the programme — mobilisation, architecture and drop windows, leadership reviews. | 84,000 |
| Lodging & boarding | 65.4 onshore person-months at a serviced-apartment-plus-per-diem basis; onshore labour rates in the commercial model are labour-only, so this cost sits in one explicit, auditable line rather than hidden inside a rate. | 240,018 |
| Local mobility & visas | UAE transport and thirty work permits. | 48,000 |
| Software licences & tooling | Monitoring and APM, code quality, test and load tooling, collaboration licences for the programme term. | 160,000 |
| UAE compliance & certification | UAE-accredited penetration testing (annual, §6.5), TDRA accessibility conformance (§5.9), data-protection and residency advisory (§7.5). | 95,000 |
| Miscellaneous & mobilisation | Insurance, communications, logistics, workspace, mobilise/demobilise. | 80,000 |
| Delivery costs |  | 767,018 |

## 2.4  Managed support — AMC Year 1, USD 568,000

From hypercare exit at the end of month eighteen — so support is never paid for twice — a staffed support pod carries the platform against the RFP’s service levels for twelve months: three offshore L2/L3 engineers, an onshore half-FTE beside the Client, half an AI/ML engineer for model drift and evaluation, half a DevOps engineer, and a half-time service delivery manager — with the monitoring and SLA-reporting stack included.

Coverage: 24/7 P1 engagement through a follow-the-sun on-call rota (response 30 minutes, resolution 2 hours, per §6.1) with staffed cover in Gulf business hours, the §6.5 patch clocks, §6.6 AI service levels including drift alerts and agent availability, and the quarterly AI adoption reporting of deliverable D12.

Per-year pricing at the Client’s option, extendable year by year:

| AMC term | Annual price (USD, 3% escalation) |
| --- | --- |
| Year 1 (included in this proposal) | 568,000 |
| Year 2 | 585,040 |
| Year 3 | 602,591 |
| Year 4 | 620,669 |
| Year 5 | 639,289 |

# 3.  How it is delivered

Fourteen months of development, drop-wise, inside a two-year delivery envelope — the full plan, lifecycle and team ramp are Section 16 of the Technical Approach Document; the skeleton is:

| Milestone | When | What the Client sees |
| --- | --- | --- |
| Mobilisation & data readiness (D0) | M0–M2 | Teams stood up, environments live, the data readiness assessment moving migration risk to month one. |
| Architecture baseline (D1) | M5 | The AI-native target architecture — microservice seams, tenancy model, LCNC design — approved. |
| Drop 1 | M7 | The registrar’s core working bilingually: master data, ships, legislation, agents A1/A3/A4/A6, UAE PASS federation. |
| Drop 2 | M11 | Seafarers; the NMC on live feeds; smart inspection with the inspector app; A2/A5/A7; GISIS and MOHRE exchanges; LCNC beta; a second port in staging. |
| Drop 3 | M14 | Ports, facilities, revenue with the payment gateway, dashboards, customer app, LCNC GA, national rollout tooling, SLA hardening. |
| Migration, UAT, Go-Live (D8, D9) | M15 = T0 | Approved migration executed with full validation; operational-readiness review; go-live. |
| Hypercare | M16–M18 | Elevated support through stabilisation; handover into the AMC. |
| KPI clocks | from T0 | Prediction accuracy at +12 months; the six Smart Inspection KPIs at +18; 80% AI-assisted coverage at +24 — each instrumented before T0, not asserted after it. |

Four clocks, one reconciliation: development runs fourteen months; go-live lands at the end of month fifteen; hypercare closes at month eighteen; the contractual delivery envelope is twenty-four months. The difference is deliberate headroom for national-rollout sequencing, not hidden work — and AMC Year 1 begins where hypercare ends.

# 4.  Payment schedule

After mobilisation, every payment follows an accepted, demonstrable milestone — and an advance bank guarantee against the mobilisation payment is offered as standard. The delivery price (total minus AMC) is USD 4,832,000; AMC Year 1 bills quarterly in arrears from its start at hypercare exit (end of month eighteen).

| Milestone | When | Share | USD |
| --- | --- | --- | --- |
| Contract signature & mobilisation | M0 | 10% | 483,200 |
| Architecture & design baseline (D1) | M5 | 10% | 483,200 |
| Drop 1 accepted | M7 | 15% | 724,800 |
| Drop 2 accepted | M11 | 15% | 724,800 |
| Drop 3 accepted | M14 | 15% | 724,800 |
| Migration approved & UAT complete | M15 | 10% | 483,200 |
| Go-Live (T0) | end M15 | 15% | 724,800 |
| Hypercare exit & operational handover | M18 | 10% | 483,200 |
| AMC Year 1 — four quarterly instalments | from M18 |  | 4 × 142,000 |
| Total |  |  | 5,400,000 |

Licence terms: the platform licence is perpetual and is granted at contract signature; its fee is recovered rateably through the blended milestone schedule and vests fully at Drop 3 acceptance. Should the engagement end before that point, amounts already paid apply first to the licence line and the Client retains the platform as delivered to date. A source-code escrow arrangement is available at the Client’s option. Invoices are payable net 30 days; the 3% AMC escalation applies from Year 2, on each anniversary of the AMC start date.

# 5.  Assumptions, exclusions and dependencies

Prices are in USD, exclusive of VAT and withholding taxes.

Azure subscription and cloud consumption are held by the Client; the model carries an option line should the Client prefer vendor-carried cloud.

Third-party onboarding and usage fees — UAE PASS, ICP, the payment gateway (the RFP names none; provider selection is confirmed at initiation), AIS/LRIT and global PSC data providers — are pass-through at cost.

AI model usage costs (inference) are pass-through; the AMC includes their monitoring, not their consumption.

The Client provides timely access to the systems and authorities the integrations depend on; every integration is stubbed in Drop 1 so build never waits, but live-feed dates gate Drop 2 content.

Effort estimates are indicative pre-detailed-design, as flagged throughout the Technical Approach Document; the fixed price is held by the parameterised model, where scope movement is absorbed by re-reconciliation, not renegotiation, within the stated envelope — movement beyond the envelope follows the change-control procedure agreed at contract.

The +18 and +24-month KPI commitments are instrumented before T0, inside the delivery price; their stewardship beyond AMC Year 1 assumes the AMC is extended — or an equivalent support arrangement is in place — through the KPI horizon.

All demonstration data in the evaluation environment is fictional; real infrastructure and public benchmarks are used where stated.

# 6.  Why this offer is credible

It is inspectable before it is signed — a zero-install demo of the full platform, and two technical documents in which every screenshot is the running build and every countable claim was counted.

The estimate has an audit trail — 944 man-weeks decomposed to line items, reconciled table by table, with counted-once boundaries stated where estimates meet.

The AI is governed, not promised — seven agents already deciding under autonomy levels, thresholds, rate caps and an append-only decision register; the national directive is answered with an operating model, not a roadmap slide.

The plan is built backwards from the RFP’s own clocks — agents live at go-live, prediction accuracy at +12 months, inspection KPIs at +18, coverage at +24 — each with the instrumentation to prove it.

The commercial model is open — one workbook, every parameter editable, the construct re-reconciling to the fixed price as terms are negotiated.

# 7.  Offer terms, validity and annexures

This proposal is issued by the System Integrator — legal entity, registered address and authorised signatory are completed on the issued copy — and is valid for 90 days from the date of issue. Prices are firm for an award within that window; beyond it they are reconfirmed through the same open commercial model rather than re-negotiated. The proposal and its annexures constitute the entire offer, are commercial-in-confidence, and are intended solely for the Client’s evaluation of this procurement. A single point of contact — name, title, e-mail and telephone — is named on the issued copy.

| Annexure | Document | Version · date |
| --- | --- | --- |
| A | Technical Approach Document — Unified Maritime Digital Services Platform | V15 · August 2026 |
| B | Sagar Drishti — Technical Approach Document | V1 · August 2026 |
| C | Commercial model workbook — CommercialModel-V1.xlsx | V1 · August 2026 |
| D | Delta-programme sizing workbook — CostingModel-DeltaProgramme.xlsx (effort-only sizing basis; superseded commercially by this proposal) | V1 · August 2026 |

Agreed and accepted:

|  | For the System Integrator | For the Client |
| --- | --- | --- |
| Name |  |  |
| Title |  |  |
| Signature |  |  |
| Date |  |  |